## Sheet1
			Project Part 4 (Due: March 16)			Project Part 5 (Due: April 7)
Goals	Project Part 2	Project Part 3	W1: Feb 22-28	W2: Mar 1-7	W3: Mar 8-14	W1: Mar 15-21	W2: Mar 15-21	W3: Mar 22-28	W4: Mar 29-Apr 4	W5: Apr 5-7			Outline	Adding Detail	Complete
Release Schedule											Estimate:
Glossary
UML for Classes, Interfaces and Relationships
Wiki
Test Cases

Use Cases: Claim (Bo, Sean)
1: UserAddClaim
2: UserDeleteClaim
3: UserEditClaim

Use Cases: Expense (Jon, Chris, Henry)
4: UserAddExpense
5: UserDeleteExpense
6: UserEditExpense

Use Cases: Tag (Bo, Sean, Jon)
7: UserAddTag
8: UserRemoveTag
9: UserRenameTag
10: UserFilterTag

Use Cases: Expense Attributes (Bo, Jon)
11: UserFlagExpense
12: UserTakePhotoOfReceipt
13: UserViewReceipt
14: UserDeletePhoto

Use Cases: Approver (Chris, Sean, Henry)
15: UserSubmitClaim
16: ApproverViewClaim
17: ApproverViewReceipt
18: ApproverCommentsClaim

Extras: (Chris, Sean, Henry, Jon, Bo)
User Accounts
Logins
Online Integration