## Sheet1
			Project Part 4 (Due: March 16)			Project Part 5 (Due: April 7)
Goals	Project Part 2	Project Part 3	W1: Feb 22-28	W2: Mar 1-7	W3: Mar 8-14	W1: Mar 15-21	W2: Mar 15-21	W3: Mar 22-28	W4: Mar 29-Apr 4	W5: Apr 5-7			Outline	Adding Detail	Complete
Release Schedule											Estimate:
Glossary
UML for Classes, Interfaces and Relationships
Wiki
Test Cases

Use Cases: Claim (Bo, Sean, Henry)
1: UserAddClaim
2: UserDeleteClaim
3: UserEditClaim

Use Cases: Expense (Jon, Chris, Henry)
4: UserAddExpense
5: UserDeleteExpense
6: UserEditExpense

Use Cases: Tag (Bo, Sean, Jon)
7: UserAddTag
8: UserRemoveTag
9: UserRenameTag
10: UserFilterTag

Use Cases: Expense Attributes (Bo, Jon, Chris)
11: UserFlagExpense
12: UserTakePhotoOfReceipt
13: UserViewReceipt
14: UserDeletePhoto

Use Cases: Approver (Chris, Sean, Henry)
15: UserSubmitClaim
16: ApproverViewClaim
17: ApproverViewReceipt
18: ApproverCommentsClaim

Extras: (Chris, Sean, Henry, Jon, Bo)
User Accounts
Logins
Online Integration

Next Iteration: (Chris, Sean, Henry, Jon, Bo)
Each Approver has their own submitted list
Undo and Redo
Data viewing features (eg. Amount spent in May)
Strengthen password security
Add salt to hashes
Add CA (certificate authority) to encrypt server
Optimize data and battery usage
Expense and Claim templates for repeat claim items